## Test Cases
Swag Labs – Test Cases
Osuji Chioma Sarah ¦ The Bug Detective – Software Testing For Beginners (STFB) ¦ Accelerated Programme ¦ saucedemo.com
Test Case ID | Module | Test Scenario | User Account | Preconditions (Before testing) | Test Steps (What to do) | Test Data (What to enter) | Expected Result (What should happen) | Actual Result (What happened) | Result (Pass/Fail/Blocked) | Bug ID (if failed)
TC-001 | Login | Successful login | standard_user | User is on the login page | 1. Enter username 2. Enter password 3. Click Login | Username: standard_user Password: secret_sauce | User redirected to products page. All 6 products visible. | User was redirected to the products page. All 6 products displayed correctly. | PASSED
TC-002 | Login | Wrong password | standard_user | User is on the login page | 1. Enter valid username 2. Enter incorrect password 3. Click Login | Username: standard_user Password: wrongpassword | Error: 'Epic sadface: Username and password do not match any user in this service' | Error message displayed as expected. User stayed on login page. | PASSED
TC-003 | Login | Invalid username | N/A | User is on the login page | 1. Enter non-existent username 2. Enter any password 3. Click Login | Username: invalid_user Password: secret_sauce | Error: 'Epic sadface: Username and password do not match any user in this service' | Error message displayed as expected. | PASSED
TC-004 | Login | Empty username field | N/A | User is on the login page | 1. Leave username blank 2. Enter any password 3. Click Login | Username: (blank) Password: secret_sauce | Error: 'Epic sadface: Username is required' | Correct error message displayed. | PASSED
TC-005 | Login | Empty password field | N/A | User is on the login page | 1. Enter valid username 2. Leave password blank 3. Click Login | Username: standard_user Password: (blank) | Error: 'Epic sadface: Password is required' | Correct error message displayed. | PASSED
TC-006 | Login | Locked out user | locked_out_user | User is on the login page | 1. Enter locked_out_user 2. Enter correct password 3. Click Login | Username: locked_out_user Password: secret_sauce | Error: 'Epic sadface: Sorry, this user has been locked out.' | Lock-out error displayed as expected. User could not access the app. | PASSED
TC-007 | Login | Login with spaces only | N/A | User is on the login page | 1. Type spaces in both fields 2. Click Login | Username: ' ' Password: ' ' | Error message appears for invalid credentials | Error message displayed. User stayed on login page. | PASSED
TC-008 | Login | Password is case-sensitive | standard_user | User is on the login page | 1. Enter valid username 2. Enter password in uppercase 3. Click Login | Username: standard_user Password: SECRET_SAUCE | Login fails with credentials mismatch error | Login failed as expected. Error message displayed. | PASSED
TC-009 | Logout | Successful logout | standard_user | User is logged in | 1. Click burger menu 2. Click Logout | N/A | User redirected to login page. Session ends. Cart cleared. | User redirected to login page. Session ended correctly. | PASSED
TC-010 | Logout | Back button after logout | standard_user | User has just logged out | 1. Press browser Back button after logout | N/A | Products page does NOT appear. User stays on login page. | Pressing Back after logout did not expose inventory. Login page remained. | PASSED
TC-011 | Product Listing | View product list | standard_user | User is logged in | 1. Observe products page after login | N/A | 6 products displayed. Each card shows image, name, description, price, Add to Cart button. | All 6 products displayed with correct images, names, descriptions, and prices. | PASSED
TC-012 | Product Listing | Open product detail | standard_user | User is logged in | 1. Click on any product name or image | Product: Sauce Labs Backpack | Product detail page opens with name, description, price, image, and Add to Cart. | Product detail page opened correctly with all expected content. | PASSED
TC-013 | Product Listing | Sort A to Z | standard_user | User is logged in | 1. Click sort dropdown 2. Select 'Name (A to Z)' | N/A | Products displayed in A–Z alphabetical order. | Products sorted correctly in A–Z order. | PASSED
TC-014 | Product Listing | Sort Z to A | standard_user | User is logged in | 1. Click sort dropdown 2. Select 'Name (Z to A)' | N/A | Products displayed in Z–A reverse alphabetical order. | Products sorted correctly in Z–A order. | PASSED
TC-015 | Product Listing | Sort price low to high | standard_user | User is logged in | 1. Click sort dropdown 2. Select 'Price (low to high)' | N/A | Products ordered cheapest to most expensive. | Products sorted correctly by price low to high. | PASSED
TC-016 | Product Listing | Sort price high to low | standard_user | User is logged in | 1. Click sort dropdown 2. Select 'Price (high to low)' | N/A | Products ordered most expensive to cheapest. | Products sorted correctly by price high to low. | PASSED
TC-017 | Product Listing | Product images load correctly | standard_user | User is logged in | 1. Observe all 6 product cards | N/A | All 6 images load and display the correct photo for each product. | All 6 images loaded and matched their respective products. | PASSED
TC-018 | Product Listing | Product descriptions visible | standard_user | User is logged in | 1. Observe all 6 product cards | N/A | All 6 products show visible description text. | All 6 descriptions were visible. | PASSED
TC-019 | Product Listing | Wrong images for problem_user | problem_user | User is logged in as problem_user | 1. Observe all 6 product cards 2. Compare each image to product name | N/A | Each product card shows the correct image matching its product name. | All 6 product cards showed the same wrong image — a dog with a ball in its mouth. Product names and prices were correct. | FAILED | BUG-001
TC-020 | Product Listing | Sort dropdown for problem_user | problem_user | User is logged in as problem_user | 1. Click anywhere on the sort dropdown 2. Select a sort option 3. Observe whether the product order changes | N/A | Sort dropdown opens, a sort option can be selected, and products reorder accordingly. | The sort dropdown opened and allowed selection of a sort option. However, selecting any option had no effect — the product order did not change. The sort control opens but does not function for this account. | FAILED | BUG-002
TC-020B | Product Listing | Sort triggers alert for error_user | error_user | User is logged in as error_user | 1. Click the sort dropdown 2. Select any sort option | N/A | Products sorted according to selected option with no errors. | Browser alert appeared: 'Sorting is broken! This error has been reported to Backtrace.' Sort did not execute. | FAILED | BUG-005
TC-020C | Product Listing | Sort order unstable for visual_user | visual_user | User is logged in as visual_user | 1. Select 'Name (A to Z)' 2. Note order 3. Switch option then reselect 'Name (A to Z)' 4. Compare | N/A | Same sort option always produces the same product order. | Sort results were inconsistent — selecting the same option at different times produced a different order each time. | FAILED | BUG-008
TC-021 | Cart | Add item to cart | standard_user | User is logged in | 1. Click 'Add to cart' on any product | Product: Sauce Labs Backpack | Button changes to 'Remove'. Cart badge shows 1. | Button changed to 'Remove'. Cart badge updated to 1. | PASSED
TC-022 | Cart | Add multiple items | standard_user | User is logged in | 1. Click 'Add to cart' on 3 different products | Products: any 3 | Each button changes to 'Remove'. Cart badge shows 3. | All 3 items added. Cart badge showed 3. | PASSED
TC-023 | Cart | Remove item from listing page | standard_user | At least 1 item in cart | 1. Click 'Remove' on a product in cart | N/A | Button reverts to 'Add to cart'. Cart badge decreases by 1. | Button reverted and badge decremented correctly. | PASSED
TC-024 | Cart | View cart contents | standard_user | At least 1 item in cart | 1. Click the cart icon | N/A | Cart page opens. All items listed with name, description, quantity (1), price, Remove button. | Cart page opened. All items displayed with correct details. | PASSED
TC-025 | Cart | Continue Shopping button | standard_user | User is on cart page with items | 1. Click 'Continue Shopping' | N/A | User returned to products page. Cart badge still shows correct count. | User returned to products page. Cart contents preserved. | PASSED
TC-026 | Cart | Cart badge stays accurate across pages | standard_user | 2 items in cart | 1. Navigate to product detail 2. Return to listing 3. Change sort order 4. Check badge | N/A | Cart badge shows 2 throughout all navigation. | Badge remained accurate at 2 across all navigation. | PASSED
TC-027 | Cart | Remove all items via cart page | standard_user | User on cart page with multiple items | 1. Click 'Remove' on each item one by one | N/A | Cart shows empty state. Cart badge disappears. | All items removed. Badge disappeared as expected. | PASSED
TC-028 | Cart | Cart limit for problem_user | problem_user | User is logged in as problem_user | 1. Click 'Add to cart' on all 6 products | N/A | All 6 products can be added to the cart. | Only 3 specific products were added. The other 3 'Add to cart' buttons were unresponsive. | FAILED | BUG-004
TC-028B | Cart | Cart limit for error_user | error_user | User is logged in as error_user | 1. Click 'Add to cart' on all 6 products | N/A | All 6 products can be added to the cart. | Only 3 specific products were added. Same 3 blocked items as problem_user. | FAILED | BUG-006
TC-029 | Checkout | Complete a full purchase | standard_user | At least 1 item in cart | 1. Cart → Checkout 2. Fill all fields 3. Continue → Finish → Back Home | First Name: Test Last Name: User Postal Code: 12345 | Confirmation page with green checkmark, thank-you message. Cart empty after Back Home. | Full checkout completed. Confirmation displayed correctly. Cart empty after Back Home. | PASSED
TC-030 | Checkout | All checkout fields empty | standard_user | On Checkout Step 1 | 1. Leave all fields empty 2. Click Continue | All fields: blank | Error: 'Error: First Name is required'. Form does not advance. | Error displayed as expected. Form did not advance. | PASSED
TC-031 | Checkout | First Name missing | standard_user | On Checkout Step 1 | 1. Leave First Name blank 2. Fill other fields 3. Click Continue | First Name: (blank) | Error: 'Error: First Name is required' | Correct error displayed. | PASSED
TC-032 | Checkout | Last Name missing | standard_user | On Checkout Step 1 | 1. Fill First Name 2. Leave Last Name blank 3. Fill Postal Code 4. Click Continue | Last Name: (blank) | Error: 'Error: Last Name is required' | Correct error displayed. | PASSED
TC-033 | Checkout | Postal Code missing | standard_user | On Checkout Step 1 | 1. Fill First Name and Last Name 2. Leave Postal Code blank 3. Click Continue | Postal Code: (blank) | Error: 'Error: Postal Code is required' | Correct error displayed. | PASSED
TC-034 | Checkout | Cancel on Step 1 goes back to cart | standard_user | On Checkout Step 1 | 1. Click Cancel | N/A | User returned to cart. Items still present. | User returned to cart page. Items were preserved. | PASSED
TC-035 | Checkout | Order summary is correct | standard_user | On Checkout Step 2 | 1. Verify items, subtotal, tax, total, payment, shipping | N/A | Items match cart. Calculations correct. Payment: SauceCard #31337. Shipping: Free Pony Express. | All details matched. Calculations were correct. | PASSED
TC-036 | Checkout | Cancel on Step 2 goes back to products | standard_user | On Checkout Step 2 | 1. Click Cancel | N/A | User returned to products page — NOT the cart. | User returned to products page as expected. | PASSED
TC-037 | Checkout | Order confirmation screen | standard_user | User has clicked Finish | 1. Observe confirmation screen | N/A | Green checkmark, 'Thank you for your order!', dispatch message, Back Home button. | Confirmation screen displayed all expected elements correctly. | PASSED
TC-037B | Checkout | Last Name overwrites First Name for problem_user | problem_user | On Checkout Step 1 as problem_user | 1. Type value in First Name 2. Click Last Name and type a value 3. Observe First Name | First Name: Test Last Name: User | Both fields accept input independently. | Typing in Last Name replaced the First Name value. Last Name remained empty. Checkout could not proceed. | FAILED | BUG-003
TC-037C | Checkout | Last Name unresponsive for error_user | error_user | On Checkout Step 1 as error_user | 1. Type value in First Name 2. Click Last Name and type a value | Last Name: User | Last Name field accepts keyboard input. | Last Name field did not respond to any input. Field remained blank. Checkout could not proceed. | FAILED | BUG-007
TC-038 | Navigation | All Items from cart | standard_user | User is on the cart page | 1. Open burger menu 2. Click All Items | N/A | User taken to the products page. | User navigated to products page correctly. | PASSED
TC-039 | Navigation | About link | standard_user | User is logged in | 1. Open burger menu 2. Click About | N/A | Sauce Labs website (saucelabs.com) loads. | Sauce Labs website loaded successfully. Link opened in the same browser tab. | PASSED
TC-040 | Navigation | Reset App State clears cart badge | standard_user | User logged in with items in cart | 1. Open burger menu 2. Click Reset App State 3. Close menu and observe | N/A | Cart badge resets to 0. Remove buttons revert to 'Add to cart'. User stays logged in. | Cart badge reset to 0. However, Remove buttons did not revert to 'Add to cart' until page was manually reloaded. Affects all users. | FAILED | BUG-012
TC-041 | Session | Session timeout redirect | standard_user | Tab left idle 30+ minutes | 1. Leave tab idle 30+ mins 2. Attempt to navigate | N/A | User redirected to login page with inline error. Expected behaviour — not a defect. | User was redirected to login page with inline error message. Behaviour confirmed as expected. | PASSED
TC-042 | Performance | Performance comparison login | performance_glitch_user | Both accounts available | 1. Time login for standard_user 2. Log out 3. Time login for performance_glitch_user | N/A | Both accounts reach products page. performance_glitch_user takes noticeably longer. | performance_glitch_user took ~3–5 seconds longer. No functional failure — performance observation only. | PASSED
TC-043 | UI / UX | Layout on smaller screens for visual_user | visual_user | User is logged in as visual_user | 1. Resize browser to 768px 2. Resize to 375px 3. Observe layout | N/A | Layout adapts responsively. All elements accessible and aligned. | Layout broke at medium and small sizes. Some elements became misaligned or inaccessible. | FAILED | BUG-009
TC-044 | UI / UX | Sort dropdown hit area | standard_user | User is logged in | 1. Hover over sort dropdown 2. Click the button background/border area (not text or icon) | N/A | Clicking anywhere within the visible button boundary opens the dropdown. | Pointer cursor showed across full button but clicks only registered on icon/text. Background area was unresponsive. | FAILED | BUG-010
Total: 49 ¦ Passed: 38 ¦ Failed: 11 ¦ Pass Rate: 78%
PASSED |  | FAILED |  | BLOCKED

## Defect Report
Swag Labs – Defect Report
Osuji Chioma Sarah ¦ The Bug Detective – Software Testing For Beginners (STFB) ¦ Accelerated Programme ¦ saucedemo.com
Defect ID | Affected Account | Module | Defect Title | Steps to Reproduce | Expected Result | Actual Result | Severity | Priority | Status | Remarks
BUG-001 | problem_user | Product Listing | [CRITICAL] All product cards display the same wrong image | 1. Log in as problem_user 2. Observe all 6 product cards 3. Compare each image to the product name | Each product card shows the correct image matching its product name | All 6 product cards showed the same wrong image — a photo of a dog with a ball. Product names and prices were correct; only images were wrong. | Critical | High | Open | Top 3 Critical #1. Ref: TC-019
BUG-002 | problem_user | Product Listing | [CRITICAL] Sort dropdown opens but does not sort | 1. Log in as problem_user 2. Click anywhere on the sort dropdown 3. Observe result | Products reorder according to the selected sort option | The sort dropdown opened and a sort option could be selected. However, selecting any option had no visible effect — products remained in the same order. The dropdown is interactive but the sort function does not execute. | Critical | High | Open | Top 3 Critical #2. Ref: TC-020
BUG-003 | problem_user | Checkout | [CRITICAL] Typing in Last Name field overwrites First Name | 1. Log in as problem_user 2. Add item → Checkout Step 1 3. Type in First Name 4. Click Last Name and type a value 5. Observe First Name | Both fields accept input independently | Typing in Last Name replaced the First Name value. Last Name stayed empty. Checkout could not proceed. | Critical | High | Open | Top 3 Critical #3. Classic input binding bug. Ref: TC-037B
BUG-004 | problem_user | Cart | [HIGH] Only 3 specific items can be added to cart | 1. Log in as problem_user 2. Click 'Add to cart' on all 6 products one by one | All 6 products can be added to the cart | Only 3 specific products were added. The other 3 'Add to cart' buttons were unresponsive — cart count did not change. | High | High | Open | Same 3 items blocked as error_user. Ref: TC-028
BUG-005 | error_user | Product Listing | [HIGH] Sorting triggers a browser alert: 'Sorting is broken!' | 1. Log in as error_user 2. Click the sort dropdown 3. Select any sort option | Products sorted according to selected option with no errors | A browser alert appeared: 'Sorting is broken! This error has been reported to Backtrace.' Sort did not execute. | High | High | Open | Only account type that surfaces an explicit error alert for sorting. Ref: TC-020B
BUG-006 | error_user | Cart | [HIGH] Only 3 specific items can be added to cart | 1. Log in as error_user 2. Click 'Add to cart' on all 6 products | All 6 products can be added to the cart | Only 3 specific products were added. Same 3 blocked items as problem_user. | High | High | Open | Same restriction as problem_user. Ref: TC-028B
BUG-007 | error_user | Checkout | [HIGH] Last Name field is completely unresponsive in checkout | 1. Log in as error_user 2. Add item → Checkout Step 1 3. Type in Last Name field | Last Name field accepts keyboard input and displays typed characters | Last Name field did not respond to any keyboard input. Field remained blank. Checkout could not proceed. | High | High | Open | Different from problem_user — field ignores input entirely rather than overwriting First Name. Ref: TC-037C
BUG-008 | visual_user | Product Listing | [HIGH] Sort order is unstable and non-deterministic | 1. Log in as visual_user 2. Select 'Name (A to Z)' 3. Note order 4. Switch option then reselect 5. Compare | Same sort option always produces the same product order | Sort results were inconsistent. Same sort option at different times produced a different order. | High | Medium | Open | All 6 items accessible — only ordering is unreliable. Ref: TC-020C
BUG-009 | visual_user | UI / UX | [MEDIUM] Layout breaks on medium to small screen sizes | 1. Log in as visual_user 2. Resize browser to 768px then 375px 3. Observe layout | Layout adapts responsively to smaller screen sizes | Some UI elements became misaligned or inaccessible at medium and small screen sizes. | Medium | Medium | Open | Compatibility/responsiveness defect. Ref: TC-043
BUG-010 | All users | UI / UX | [MEDIUM] Sort dropdown has an incomplete click hit area | 1. Hover over the sort dropdown 2. Click the button background/border area (not text or icon) | Clicking anywhere within the visible button boundary opens the dropdown | Pointer cursor appeared across the full button but clicks only registered on the icon or text label. Button background area was unresponsive. | Medium | Low | Open | Affects all users. CSS hit-area bug. Ref: TC-044
BUG-011 | Any | Session | [MEDIUM] Session expiry error message uses raw URL path | 1. Log in 2. Leave idle 30+ minutes 3. Attempt to navigate | A clear user-friendly message such as: 'Your session has expired. Please log in again.' | Error message read: 'You can only access /cart.html when you are logged in.' Redirect was correct but message is not user-friendly. | Medium | Low | Open | Session redirect is correct — UX wording issue only. Ref: TC-041
BUG-012 | All users | Navigation | [MEDIUM] Reset App State resets badge but Remove buttons don't revert until page reload | 1. Log in and add items to cart 2. Burger menu → Reset App State 3. Close menu and observe product buttons | Cart badge resets to 0 AND Remove buttons immediately revert to 'Add to cart' | Cart badge correctly reset to 0. However, product buttons continued to show 'Remove' until the page was manually reloaded. Affects all user accounts. | Medium | Medium | Open | Ref: TC-040
BUG-013 | Any | Navigation | [LOW] No visual confirmation after Reset App State | 1. Log in 2. Add items 3. Burger menu → Reset App State | A brief confirmation message appears confirming the reset | No confirmation shown. Cart silently cleared with no user feedback. | Low | Low | Open | UX observation only.
BUG-014 | Any | Checkout | [LOW] Order confirmation page lacks an order reference number | 1. Complete a full checkout 2. Observe confirmation screen | Confirmation shows an order number or reference | Only a generic thank-you message shown. No order number or trackable reference. | Low | Low | Open | Expected limitation of demo app.
Severity Legend (left) ¦ Status Legend (right)
Critical | High | Medium | Low | Open | Fixed | Deferred | Closed

## Test Summary Report
Swag Labs – Test Summary Report
Osuji Chioma Sarah ¦ The Bug Detective – Software Testing For Beginners (STFB) ¦ Accelerated Programme ¦ saucedemo.com
Field | Details
Project Name | Swag Labs Manual QA Testing – The Bug Detective – Software Testing For Beginners (STFB) ¦ Accelerated Programme
Application URL | https://www.saucedemo.com
Application Type | Web-Based E-Commerce Demo (Sauce Labs)
Prepared By | Osuji Chioma Sarah
Report Date | [ Add date ]
Test Period | [ Fill in start date ] to [ Fill in end date ]
Total Test Cases Planned | 49
Total Test Cases Executed | 49
Total Defects Found | 14
Overall Pass Rate | 78% (38 of 49 test cases passed)
Test Execution Results by Module
Module | Total TCs | Passed | Failed | Blocked | Pass Rate
Login | 8 | 8 | 0 | 0 | 100%
Logout | 2 | 2 | 0 | 0 | 100%
Product Listing | 14 | 8 | 6 | 0 | 57%
Cart | 9 | 7 | 2 | 0 | 78%
Checkout | 11 | 9 | 2 | 0 | 82%
Navigation | 3 | 2 | 1 | 0 | 67%
Session | 1 | 1 | 0 | 0 | 100%
Performance | 1 | 1 | 0 | 0 | 100%
TOTAL | 49 | 38 | 11 | 0 | 78%
Defect Summary by Severity
Severity | Count | Key Defects | Status
Critical | 3 | BUG-001 (wrong images on all cards), BUG-002 (sort dropdown opens but does not sort), BUG-003 (Last Name overwrites First Name) — all problem_user | Open
High | 5 | BUG-004 (cart limit – problem_user), BUG-005 (sort alert – error_user), BUG-006 (cart limit – error_user), BUG-007 (Last Name unresponsive – error_user), BUG-008 (unstable sort – visual_user) | Open
Medium | 4 | BUG-009 (layout breaks on small screens – UI/Compatibility), BUG-010 (sort dropdown incomplete hit area – UI/UX), BUG-011 (session message wording), BUG-012 (Reset App State button revert – all users) | Open
Low | 2 | BUG-013 (no reset confirmation), BUG-014 (no order reference) | Open
TOTAL | 49 | 38 | 11 | 0 | 78%
Top 3 Critical Issues
Rank | Defect ID | Title | Account | Impact | Recommendation
#1 | BUG-001 | All 6 product cards show the same wrong image | problem_user | Users cannot identify any product — all cards show a dog photo | Fix image-product mapping; verify all 6 cards after fix
#2 | BUG-002 | Sort dropdown opens but does not sort | problem_user | Users cannot sort the product catalogue at all | Fix sort dropdown event binding for problem_user
#3 | BUG-003 | Last Name input overwrites First Name in checkout | problem_user | Checkout cannot be completed — both name fields can never be simultaneously filled | Fix input field binding — both fields share the same state variable
Overall Assessment
Test Coverage | 49 test cases designed and executed across 8 modules. All 5 user account types tested: standard_user, locked_out_user, problem_user, error_user, and visual_user.
Pass Rate | 78% — 38 of 49 test cases passed. 11 test cases failed, all linked to intentional defects in problem_user, error_user, and visual_user accounts.
standard_user | All features functioned correctly. Login, cart, checkout, navigation, and session all passed. Used as the baseline for cross-account comparisons.
problem_user | 3 Critical + 2 High defects. Wrong images on all 6 cards, sort dropdown opens but does not sort, Last Name overwrites First Name in checkout. Cart restricted to 3 specific items.
error_user | 3 High defects. Sort triggers an explicit browser alert. Last Name field unresponsive in checkout. Cart restricted to 3 specific items — same items as problem_user.
visual_user | 2 defects. Sort order is non-deterministic — changes each time the same option is selected. Layout breaks on smaller screen sizes. All 6 cart items work correctly.
All Users | 2 defects affect all accounts: Reset App State resets badge to 0 but Remove buttons don't revert to 'Add to cart' until page reload (BUG-012). Sort dropdown has an incomplete click hit area (BUG-010).
Recommendation | Application serves its purpose as a QA training tool. All defects appear intentional. standard_user experience is fully stable. Test cycle complete.

## Template 1 – Feature Inventory
Template 1: Feature Inventory
Osuji Chioma Sarah ¦ The Bug Detective – Software Testing For Beginners (STFB) ¦ Accelerated Programme ¦ saucedemo.com
Feature Area | Feature | Sub-feature | What the app should do (Expected Behaviour) | How to test it (Test Steps / Scenarios) | Priority | Tester's Notes
Login | Authentication | Valid login | When a tester enters a valid username and the password 'secret_sauce', the app should take them straight to the products page. | Try logging in with each of the 6 valid usernames one at a time using the password 'secret_sauce'. Confirm the products page loads each time. | High | There is no way to create a new account — all usernames are pre-set.
|  | Wrong password | If the correct username is entered but the password is wrong, the app should show an error message saying the username and password do not match. | Enter a valid username with an incorrect password (e.g., 'wrongpass'). Confirm the error message appears and the products page does NOT load. | High
|  | Locked-out user | When 'locked_out_user' tries to log in, the app should block them and show: 'Epic sadface: Sorry, this user has been locked out.' | Log in using the username 'locked_out_user' with the correct password. Confirm the exact lock-out error message appears. | High | The error message must match word-for-word, including capitalisation.
|  | Empty username or password | If the username or password field is left blank, the app should show an error telling the tester which field is missing. | Try submitting the login form with: (1) both fields empty, (2) only username empty. Confirm an error appears for each blank field. | High
Product Listing | Display | Product images | Each product on the listing page should show the correct image. For 'standard_user', all 6 images should be accurate. For 'problem_user', the images will be wrong (showing unrelated photos) — this is an intentional bug to find. | Log in as 'standard_user' and note all 6 product images. Then log in as 'problem_user' and compare — the images should look different/wrong for problem_user. | Medium | IMPORTANT UPDATE: problem_user shows wrong images (e.g., a dog photo instead of a backpack), NOT broken/missing images. The images load but display the incorrect product photo.
|  | Product info | Every product card should clearly show the product name, a short description, and the price. | Check all 6 product cards on the listing page. Confirm each one has a visible name, description, and price. | Medium
| Sorting | Name A to Z | When 'Name (A to Z)' is selected from the sort dropdown, products should be listed in alphabetical order from A to Z. This is also the default order when you first log in. | Log in as 'standard_user', confirm default order is A–Z. Then manually select 'Name (A to Z)' and confirm the order matches. Note: sorting does NOT work for 'problem_user' — this is an intentional bug. | Medium | Sorting is broken for problem_user — selecting any sort option does nothing. Log this as a defect when testing with that account.
|  | Name Z to A | When 'Name (Z to A)' is selected, products should be listed in reverse alphabetical order. | Select 'Name (Z to A)' from the sort dropdown. Confirm the last product alphabetically now appears first. | Medium
|  | Price low to high | When 'Price (low to high)' is selected, the cheapest product should appear first and the most expensive last. | Select 'Price (low to high)' from the sort dropdown. Confirm products are ordered from cheapest to most expensive. | Medium
|  | Price high to low | When 'Price (high to low)' is selected, the most expensive product should appear first. | Select 'Price (high to low)' from the sort dropdown. Confirm products are ordered from most expensive to cheapest. | Medium
| Add to Cart | Adding a single item | When the 'Add to cart' button is clicked on any product, the cart icon at the top right should show a number badge counting the item, and the button should change to 'Remove'. | Click 'Add to cart' on one product. Check that: (1) the button changes to 'Remove', and (2) the cart icon shows the number 1. | High | There is no option to add more than 1 of the same item.
|  | Removing an item | When the 'Remove' button is clicked, the item should be taken out of the cart, the badge count should go down by 1, and the button should change back to 'Add to cart'. | After adding an item, click 'Remove'. Check that the button reverts and the cart badge count decreases. | High
Cart | View Cart | Cart contents display | When the cart page is opened, it should list every item that was added, showing the product image, name, description, quantity (always 1), price, and a Remove button. | Add 2–3 products to the cart, then click the cart icon. Confirm all added products appear with correct details. | High | The quantity is always 1 per item — there is no way to increase it.
|  | Continue Shopping button | Clicking 'Continue Shopping' from the cart page should take the user back to the products page, with all previously added items still in the cart. | Add items to cart, go to cart page, click 'Continue Shopping'. Confirm: (1) you land on the products page, and (2) the cart badge still shows the correct count. | Medium
| Cart Badge | Badge count stays accurate | The cart badge number should always show the correct count of items, no matter which page you navigate to, whether you change the sort order, or whether you view a product detail page. | Add 2 items to the cart. Navigate to: a product detail page, back to the listing, change the sort order, then go back to the cart. Confirm the badge shows 2 throughout. | Medium | This is a cross-feature check — the badge must stay accurate across all navigation actions.
Checkout | Step 1 – Customer Info Form | All fields are required | On the first checkout screen, there are three fields: First Name, Last Name, and Zip/Postal Code. All three must be filled in before the form will move to the next step. If any field is left empty and the tester clicks 'Continue', an error message should appear identifying the empty field (e.g., 'Error: First Name is required'). | Go to checkout Step 1. Test these combinations one at a time: 1. Leave all 3 fields empty → click Continue 2. Fill only First Name → click Continue 3. Fill only Last Name → click Continue 4. Fill only Zip → click Continue 5. Fill First + Last, leave Zip empty → click Continue 6. Fill First + Zip, leave Last empty → click Continue 7. Fill Last + Zip, leave First empty → click Continue Confirm the correct error message appears each time. | High | The zip/postal code field accepts any text — there is no format check (e.g., you can type 'abc' and it will be accepted). Error messages must match exactly.
|  | Cancel button on Step 1 | Clicking 'Cancel' on the Step 1 form should take the user back to the cart page — not the products page. | Go to checkout Step 1 and click Cancel without filling in any fields. Confirm you land on the cart page with your items still there. | Medium
|  | Continue button on Step 1 | When all three fields are filled in, clicking 'Continue' should move the user to the order review screen (Step 2). | Fill in First Name, Last Name, and Zip/Postal Code, then click Continue. Confirm the order review screen loads. | High
| Step 2 – Order Review | Order summary display | The order review screen should show: all the items in the cart with their prices, the payment method (always shown as 'SauceCard #31337'), the shipping method (always shown as 'Free Pony Express Delivery!'), a subtotal before tax, the tax amount, and the final total including tax. | Add 2 products to the cart, go through checkout Step 1, and arrive at Step 2. Check that: (1) both products are listed, (2) payment and shipping info appear, (3) the item total matches the sum of product prices, and (4) tax is shown and the final total = item total + tax. | High | Payment and shipping details are placeholders — no real payment is processed.
|  | Cancel button on Step 2 | Clicking 'Cancel' on the order review screen should take the user back to the products page — NOT back to the cart. | On the Step 2 review screen, click Cancel. Confirm you land on the products listing page. | Medium | Note: this is different from Step 1's Cancel button, which goes back to the cart.
|  | Finish button | Clicking 'Finish' should complete the order and take the user to the order confirmation screen. | On the Step 2 review screen, click Finish. Confirm the order confirmation page loads. | High
| Step 3 – Order Confirmation | Success message | After finishing an order, the app should show a confirmation screen with a green checkmark icon, the message 'Thank you for your order!', and the text 'Your order has been dispatched, and will arrive just as fast as the pony can get there!' along with a 'Back Home' button. | Complete a full checkout flow and reach Step 3. Confirm: (1) the green checkmark icon is visible, (2) the 'Thank you for your order!' heading appears, (3) the dispatch message appears, and (4) the 'Back Home' button is present and clickable. | High | The confirmation page shows a green checkmark icon — NOT a pony image as previously noted. Updated based on direct observation.
|  | Back Home button | Clicking 'Back Home' should take the user back to the products page and the cart should be completely empty. | After completing an order, click 'Back Home'. Confirm: (1) you are on the products page, and (2) the cart badge is gone (cart is empty). | High
Navigation | Burger Menu | All Items link | Clicking 'All Items' in the side menu should take the user back to the products listing page from any screen. | Open the burger menu from the cart page, checkout Step 1, Step 2, and the confirmation page. Each time, click 'All Items' and confirm the products page loads. | Medium
|  | About link | Clicking 'About' in the side menu should take the user to the Sauce Labs website (https://saucelabs.com). | Open the burger menu and click 'About'. Confirm the Sauce Labs website loads and the URL is correct. | Low | UNRESOLVED: It is unclear whether this should open in the same browser tab or a new tab. This needs a decision from the Team Lead before a pass/fail result can be recorded.
|  | Logout | Clicking 'Logout' should end the user's session, clear the cart, and redirect to the login page. | Add items to the cart, open the burger menu, and click Logout. Confirm: (1) the login page appears, and (2) logging back in shows an empty cart. | High
|  | Reset App State | Clicking 'Reset App State' in the burger menu should clear all items from the cart without logging the user out. The page should not show any confirmation — it just resets silently. | Add items to the cart, open the burger menu, click 'Reset App State', then close the menu. Confirm the cart badge is gone and the products page shows 'Add to cart' buttons (not 'Remove'). | Medium | No confirmation message is shown — the reset happens silently. Particularly useful when testing with problem_user to return the app to a clean state.
Error & Session | Performance | Slow load times with performance_glitch_user | When logged in as 'performance_glitch_user', all actions (login, adding to cart, navigating) should still work correctly but will take noticeably longer than with 'standard_user' — typically more than 2 seconds per action. | Log in as 'standard_user' and time how long each of these actions takes: login, add-to-cart, navigate to cart, go to checkout Step 1. Then repeat the same steps logged in as 'performance_glitch_user'. Compare the times for each action. | Medium | This is an exploratory test — there is no fixed time limit that counts as a pass or fail. Just record and compare the timings. Flag any action that takes more than 2 seconds longer than standard_user.
| Session | Back button after logout | After logging out, if the user presses the browser's Back button, the app should NOT show the products page or their previous cart. The user should stay on or be returned to the login page. | Log in, add items to cart, then log out. Press the browser Back button. Confirm the products page does NOT appear — you should see the login page or an access-denied message. | High | SECURITY TEST — If the products page is visible after logout, this is a high-severity security defect. Log it immediately with Member 9.
Problem User | Defect Exploration | Testing all features with problem_user | The 'problem_user' account is specifically set up to have bugs in it. When testing with this account, testers should expect to find: (1) wrong product images — photos of unrelated items appear instead of the correct product, (2) sorting does nothing when a sort option is selected, (3) adding a product to the cart may add a different item than the one clicked, and (4) some checkout form fields may not accept typing. | First complete a full test run with 'standard_user' to know what correct behaviour looks like. Then log in as 'problem_user' and repeat the same steps. At each step, note any difference from standard_user and record it as a defect with a screenshot. | High | Every difference from standard_user behaviour should be logged as a separate defect report. Expected defects to find: wrong images, broken sort, wrong cart item, unresponsive form fields.
Error & Session | Session | Session timeout / expiry | If the browser tab is left open but idle for a long time (30+ minutes without any clicks or actions), the app will automatically log the user out in the background. The next time the user tries to do anything — like adding to cart — the app will redirect them to the login page and show a message explaining they need to log in again. | Log in and add an item to the cart. Leave the browser tab open but do not click anything for at least 30 minutes. Then try to add another item or navigate to another page. Confirm you are sent to the login page and an inline error message appears. | Medium | This is EXPECTED and CORRECT behaviour — it is not a bug. The redirect is graceful. The error message may say something like 'You can only access /cart.html when you are logged in' — this is intentional.
Priority Legend:
High – must be tested |  | Medium – should be tested |  | Low – test if time allows

## Template 2 – Business Rules
Template 2: Business Rules & Constraints
Osuji Chioma Sarah ¦ The Bug Detective – Software Testing For Beginners (STFB) ¦ Accelerated Programme ¦ saucedemo.com
Rule ID | Category | Rule Description | Priority | Related Feature | Test Implication | Status
BR-01 | Authentication | Only 6 pre-defined usernames work; no new user registration possible | High | Login | Cannot test a registration flow – remove from scope | Confirmed
BR-02 | Authentication | All valid accounts share the same password: secret_sauce | High | Login | No password change functionality to test | Confirmed
BR-03 | Authentication | locked_out_user always fails with exact error: 'Epic sadface: Sorry, this user has been locked out.' | High | Login | Error string must match exactly – case-sensitive assertion required | Confirmed
BR-04 | Cart | Quantity per line item is always 1; no increment/decrement control | Medium | Cart | Cannot test bulk-add or quantity update scenarios | Confirmed
BR-05 | Checkout | Payment is always 'SauceCard #31337' – no real payment processing | High | Checkout | No payment failure or decline scenarios possible | Confirmed
BR-06 | Checkout | Shipping is always 'Free Pony Express Delivery!' – static placeholder | Low | Checkout | Verify text displays correctly; no shipping cost logic to test | Confirmed
BR-07 | Product Data | problem_user account shows wrong product images — unrelated photos appear instead of the correct product image (e.g., a dog photo instead of a backpack). The images load successfully but display the wrong content. | Medium | Product Listing | UI/UX tester (Member 10) must visually compare each product image when logged in as problem_user vs standard_user. Log each mismatch as a separate defect. | Confirmed
BR-08 | Performance | performance_glitch_user has intentional delays (>2 s) on all actions | Medium | All Features | Member 11 should measure and log timings; no formal timeout SLA defined – treat as exploratory | Confirmed
BR-09 | Security | After logout, browser back button must NOT expose the previous user's inventory or cart | High | Navigation / Session | Manual tester (Member 6) to verify; a failure here is a HIGH severity defect | Confirmed
BR-10 | Error Handling | Empty required checkout fields show specific errors: 'Error: First Name is required', etc. | High | Checkout | Exact error text required for assertion – case sensitive | Confirmed
BR-11 | External Links | 'About' menu item links to https://saucelabs.com | Low | Navigation | Verify URL and that the link is reachable; tab behaviour (same vs new) is AMBIGUOUS – flag for Team Lead | Open – Needs Clarification
BR-12 | Cart | Cart badge count persists across page navigation, sort changes, and detail page views within the same session | Medium | Cart / Navigation | Member 8 owns cross-feature cart persistence test (previously unassigned) | Confirmed
BR-13 | Product Data | problem_user may add a different item than the one clicked (intentional defect) | High | Cart | Member 7/9 must compare items added via problem_user vs standard_user to confirm and log defect | Confirmed
BR-15 | Security / UX | After session expiration due to inactivity, the app redirects the user to the login page and displays an inline error identifying the protected route that was accessed (e.g., '/cart.html'). Session invalidation is handled gracefully. | Medium | Navigation / Session | Session handling confirmed as correct — NOT a defect. Member 10 (UI/UX Tester) should note whether the error wording could be improved (e.g., 'Your session has expired. Please log in again.'). Member 6 to include in session test execution. | Confirmed

## Template 3 – User Flows
Template 3: User Flow Summary
Osuji Chioma Sarah ¦ The Bug Detective – Software Testing For Beginners (STFB) ¦ Accelerated Programme ¦ saucedemo.com
Flow ID | Flow Name | Type | Steps (Happy Path) | Alternate Paths | Preconditions | Postconditions | Pass / Fail Criteria
F-01 | Successful Purchase | Happy Path | Login → Add item(s) to cart → View cart → Click Checkout → Fill First Name, Last Name, Postal Code → Continue → Review order → Finish → Back Home | 1. Remove item before checkout and re-add 2. Cancel during Step 1 → return to cart 3. Cancel during Step 2 → return to inventory | User not logged in; cart is empty | User returned to inventory page; cart badge is gone (cart is empty) | Order confirmation page shown with 'Thank you for your order!'; cart empties after Back Home
F-02 | Locked User Login Attempt | Negative / Error | Navigate to login page → Enter 'locked_out_user' + 'secret_sauce' → Click Login → Error message displayed | N/A | User not logged in | User remains on login page; no inventory access | PASS: Error reads exactly 'Epic sadface: Sorry, this user has been locked out.' FAIL: Any other message or if inventory loads
F-03 | Checkout Form Validation | Negative / Error | Login → Add item → Checkout → Arrive at Step 1 → Leave one or more fields empty → Click Continue → Error displayed → Form stays open | Test all 7 combinations: all 3 empty; each field empty individually; any 2 empty | Cart has ≥1 item; user is on Checkout Step 1 | Form is NOT submitted; error message is displayed; user remains on Step 1 | PASS: Correct field-specific error shown (e.g., 'Error: First Name is required') FAIL: Form submits with empty fields; wrong error shown; no error shown
F-04 | Logout and Session Security | Security | Login → Add item to cart → Open burger menu → Click Logout → Verify login page shown → Press browser Back button → Verify inventory is NOT accessible | 1. Reset App State before logout and verify cart cleared 2. Logout without items in cart | User is logged in | Session ended; login page shown; browser back does not expose inventory | PASS: Back button returns to login page or shows blank/error FAIL: Inventory page accessible after logout (HIGH SEVERITY – see BR-09)
F-05 | Performance Comparison | Exploratory | Login as standard_user → Perform: login, add-to-cart, navigate to cart, proceed to checkout Step 1 → Record elapsed time for each step Repeat identically with performance_glitch_user → Compare timings | Run each user scenario 3 times to get average; clear cache between runs | Fresh login for each run; no items in cart at start | Timing log recorded for both users per action | EXPLORATORY – No binary pass/fail. Log timings and flag any action where performance_glitch_user exceeds standard_user by >2 seconds. Refer to BR-08.
F-06 | Problem User Defect Exploration | Defect Exploration | Login as problem_user → Observe product listing (note any broken/wrong images) → Attempt to sort products → Add item to cart (note actual item added vs clicked) → Proceed through checkout → Attempt to fill form fields | Run same sequence with standard_user first to establish baseline for comparison | Baseline run with standard_user completed and documented | All defects observed are logged to Member 9 (Defect Manager) with screenshots and steps to reproduce | No binary pass/fail – DEFECT EXPLORATION flow. Each deviation from standard_user behaviour = one defect report. Minimum expected defects: broken images, wrong cart item, sort failure. Refer to BR-07 and BR-13.
F-07 | Cart Badge Persistence | Cross-Feature | Login → Add 2 items → Note badge count (2) → Navigate to product detail page → Return to listing → Change sort order → Navigate to cart → Return to listing → Verify badge still shows 2 | 1. Remove one item mid-flow and verify badge decrements 2. Refresh page and verify badge persists | User is logged in; at least 2 items added to cart | Cart badge reflects accurate item count throughout all navigation actions | PASS: Badge count accurate at every step FAIL: Badge resets, disappears, or shows wrong count at any point. Refer to BR-12.
F-08 | Session Expiration Handling | Security / Negative | Login as standard_user → Add item to cart → Leave browser tab idle for 30+ minutes (do not interact) → Attempt to add another item or navigate to a protected page → Observe behaviour | N/A – linear flow | User is logged in; at least 1 item in cart; tab left idle for 30+ minutes | User is on the login page; inline error is displayed; cart state is cleared | PASS: User redirected to login page with inline error explaining the protected route FAIL: App crashes, shows blank page, or allows continued access without re-authentication UX NOTE (Member 10): Flag if error wording is not user-friendly (e.g., suggest 'Session expired' messaging). Ref: BR-15.